## Plan
Task | Owner | Start | End | Days | Status | % complete
Kick-off and scope | Alex | 2026-08-03 | 2026-08-05 |  | Done | 100%
Research | Sam | 2026-08-06 | 2026-08-13 |  | In progress | 60%
First draft | Alex | 2026-08-14 | 2026-08-21 |  | Not started | 0%
Review | Jo | 2026-08-22 | 2026-08-25 |  | Not started | 0%
Handover | Sam | 2026-08-26 | 2026-08-28 |  | Not started | 0%
Overall

## How to use
How to use this template
Days is end minus start in calendar days — it does not exclude weekends.
Keep the Status wording consistent ("Done") or the count in the Overall row will miss rows.
Overall % complete is a plain average of the task percentages; weight it yourself if some tasks are much bigger.
Insert new tasks ABOVE the Overall row so every range grows with them.
Free from FormulaSmith — https://formulasmith.com/en/templates/