## RACI matrix
Work item | Sponsor | Product | Design | Engineering | Marketing | Check
Scope and priorities | A | R | C | I | I
Requirements | A | R | C | C | I
UI design | C | A | R | C | I
Implementation | I | C | A | R | I
Quality assurance | I | C | A | R | I
Launch approval | A | R | C | C | I
Release communications | A | C | I | I | R
Ready tasks

## RACI key
Code | Meaning | Decision rule
R | Responsible | Does the work; at least one R per task
A | Accountable | Owns final decision; exactly one A per task
C | Consulted | Asked for input before the work or decision
I | Informed | Updated on progress or outcome
A/R | Accountable and responsible | One role carries both ownership and the work

## How to use
How to use this template
Rename the five role headers to your real team roles.
Put A, R, C or I in each role cell; use A/R when one role does both. Leave irrelevant roles blank.
The Check column flags tasks with zero/multiple A assignments or with no R.
Exactly one accountable role per row, including A/R cells; duplicate A assignments are flagged.
Insert new tasks above the Ready tasks summary and extend the formulas when required.
Free from FormulaSmith — https://formulasmith.com/en/templates/